## Simple Gantt Chart - BLANK
Project Schedule
PROJECT TITLE | Root 9 Group Project
PROJECT MANAGER | N/A
COMPANY NAME | Root 9
Gantt Schedule (Week starting at date mentioned)
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | 2023-10-23 | [6 empty] | 2023-10-30 | [6 empty] | 2023-11-06
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Project Conception
1.1 | SDLC Choice | Taiga |  |  |  | 100%
1.1.1 | Framework Selection | Taiga |  |  |  | 0%
1.2 | Selecting purpose of project | Anna |  |  |  | 0%
1.3 | Technologies for Project | Group |  |  |  | 0%
1.4 | Selecting APIs | Group |  |  |  | 0%
1.4.1 | API choices for colors | N/A |  |  |  | 0%
1.4.2 | API choices for image upload | N/A |  |  |  | 0%
1.4.3 | Other API choices | Group |  |  |  | 0%
2 | Project Plan Details
2.1 | Planned Features for each API | N/A |  |  |  | 0%
2.2 | Wireframes and Prototypes | Anna |  |  |  | 0%
2.3 | User Stories | N/A |  |  |  | 0%
2.4 | Data Flow Diagrams | Anna |  |  |  | 0%
3 | Project Plan Documentation
3.1 | Work Breakdown Structure | Stefan | 2023-10-27 | 2023-11-03 | 7 | 50%
3.2 | Project Schedule/Timeline | Cindy |  |  |  | 0%
3.3 | Project Report Finalization | N/A |  |  |  | 0%
4 | Project Plan Report Presentation
4.1 | Choose platform for presentation | Group |  |  |  | 0%
4.2 | Create presentation of report | N/A |  |  |  | 0%
4.3 | Divide sections of presentation | Group |  |  |  | 0%
4.4 | Record presentation | Group |  |  |  | 0%
5 | Finalizations and Submission
5.1 | Check for spelling and grammar errors | N/A |  |  |  | 0%
5.2 | Make sure all links in PDF are working | N/A |  |  |  | 0%
5.3 | Final Submission | N/A |  |  |  | 0%