## WBS Outline & Diagram
PROJECT TITLE | Root 9 Group Project | CLASS | CMPT 276
PROJECT MGR | Taiga | DATE | 10/30/23
| OUTLINE |  |  |  |  | Task # | Task Title | Assigned Group Member | Expected Time (in Hours) | Actual Time (in Hours) | Task # | Task Title | Assigned Group Member | Expected Time (in Hours) | Actual Time (in Hours)
| Task # | Task Title | Assigned Group Member | Expected Time (in Hours) | Actual Time (in Hours) | 2 | Coding/Implementation |  |  |  | 3 | Final Documentation
| 1 | Project Planning |  |  |  | 2.1 | Import Necessary APIs |  |  |  | 3.1 | Create Final Project Report
| 1.1 | Team Setup |  |  |  | 2.1.1 | Import Cloudinary | Taiga | 0.5 | TBA | 3.1.1 | Identify lessons learned from project | Group | 2 | TBA
| 1.1.1 | Establish team communication | Group | 1 | 1 | 2.1.2 | Import Colormind | Taiga | 0.5 | TBA | 3.1.2 | Include information which is required | Group | 4 | TBA
| 1.1.2 | Split up team roles and work assignment | Group | 1 | 1 | 2.1.3 | Import Imagga Color Extraction | Taiga | 0.5 | TBA | 3.1.3 | Place necessary links and files | Group | 1 | TBA
| 1.1.3 | Team Setup Complete |  | 2 | 2 | 2.1.4 | Import Necessary APIs Complete |  | 1.5 | 0 | 3.1.4 | Final spelling and grammatical check | Group | 1 | TBA
| 1.2 | Technical Requirements |  |  |  | 2.2 | Create Layout and General Features |  |  |  | 3.1.5 | Create Final Project Report Complete |  | 8 | 0
| 1.2.1 | SDLC Selection | Taiga | 1 | 1 | 2.2.1 | Develop header and navigation functionality | Anna/Cindy | 0.5 | TBA | 3.2 | Create Final Presentation
| 1.2.2 | Technology Stack Selection | Taiga | 1 | 1 | 2.2.1.1 | Ensure Mobile Responsiveness | Anna/Cindy | 1 | TBA | 3.2.1 | Create presentation slides | Group | 1 | TBA
| 1.2.3 | Choose APIs for color extraction | Taiga | 1 | 0.5 | 2.2.2 | Test header and navigation functionality | Anna/Cindy | 1 | TBA | 3.2.2 | Create project demo video | Group | 2 | TBA
| 1.2.4 | Choose APIs for image uploading | Taiga | 1 | 0.5 | 2.2.3 | Page structure and layout | Anna/Cindy | 0.5 | TBA | 3.2.3 | Include information which is required | Group | 2 | TBA
| 1.2.5 | Determine features for each API | Taiga/Group | 2 | 1.5 | 2.2.3.1 | Implement layout grids and spacing | Anna/Cindy | 1 | TBA | 3.2.4 | Practice presentation to stay in time limit | Group | 4 | TBA
| 1.2.6 | Setup Github and Github Actions | Stefan | 1 | 0.5 | 2.2.3.2 | Optimize layout for different screen sizes | Anna/Cindy | 0.5 | TBA | 3.2.5 | In class presenation | Group |  | TBA
| 1.2.7 | Setup Figma, the work enviroment. | Anna | 0.5 | 0.1 | 2.2.4 | Test page structure and layout | Anna/Cindy | 1.5 | TBA | 3.2.6 | Create Final Presentation Complete |  | 9 | 0
| 1.2.8 | Technical Requirements Complete |  | 7.5 | 5.1 | 2.2.5 | Error handling and validation | Anna/Cindy | 0.5 | TBA | 3.3 | Final Submission
| 1.3 | Project Plan Details |  |  |  | 2.2.6 | Exporting & Saving functionality | Anna/Cindy | 3.5 | TBA | 3.3.1 | Check project requirements for web application | Group | 3 | TBA
| 1.3.1 | Create User Stories | Group | 2 | 0.5 | 2.2.7 | Create Layout and General Features Complete |  | 10 | 0 | 3.3.2 | Check for general quality (spelling, grammar) | Group | 2 | TBA
| 1.3.2 | Wireframe and Prototype | Anna |  |  | 2.3 | Implement Main Colour Extractor |  |  |  | 3.3.3 | Check project requirements for report and presentation | Group | 2 | TBA
| 1.3.2.1 | Research industry practices | Anna | 1 | 1 | 2.3.1 | Research color extraction algorithms | Group | 0.5 | TBA | 3.3.4 | Check for general quality (spelling, grammar) | Group | 1 | TBA
| 1.3.2.2 | Low-fidelity wireframing | Anna |  |  | 2.3.2 | Select API for color extraction | Group | 0.5 | TBA | 3.3.5 | Confirm repository has all required files | Group | 1 | TBA
| 1.3.2.2.1 | Create wireframes | Anna | 1 | 1 | 2.3.3 | Setup API Environment | Group | 0.5 | TBA | 3.3.6 | Final Submission Complete |  | 9 | 0
| 1.3.2.2.2 | Review and iterate wireframes | Anna | 1 | 0.3 | 2.3.4 | Develop color extraction function | Group | 4 | TBA | 3.4 | Final Documentation Complete |  | 9 | 0
| 1.3.2.2.3 | Approve the layout | Anna | 0.5 | 0.5 | 2.3.5 | Integrate color extraction with frontend | Group | 2.5 | TBA
| 1.3.2.3 | High-fidelity prototyping | Anna |  |  | 2.3.6 | Test color extraction feature | Group | 1 | TBA
| 1.3.2.3.1 | Create UI elements and components | Anna | 2 | 3 | 2.3.7 | Implement error handling and edge cases | Group | 1 | TBA
| 1.3.2.3.2 | Create high-fidelity versions of prototypes | Anna | 5 | 7 | 2.3.8 | Test with users and collect feedback | Group | 1.5 | TBA
| 1.3.2.3.3 | Add interactivity to prototypes | Anna | 2 | 1 | 2.3.9 | Implement Main Colour Extractor Complete |  | 11.5 | 0
| 1.3.2.4 | Test prototypes for usability | Anna | 0.5 | 0.5 | 2.4 | Moodboard creation and Drag & Drop
| 1.3.2.5 | Document design specifications, interactions, and guidelines | Anna | 0.5 | 0.25 | 2.4.1 | Implement Drag & Drop functionality | Group | 3.5 | TBA
| 1.3.3 | Data Flow Diagram |  |  |  | 2.4.2 | Create Mood Board Arrangement features | Group | 3.5 | TBA
| 1.3.3.1 | Sketch Data Flow Diagram Blueprint | Cindy | 0.5 | 0.5 | 2.4.3 | Moodboard creation and Drag & Drop Complete |  | 7 | 0
| 1.3.3.2 | Create Data Flow Based on Users' Perpectives | Cindy | 1 | 0.5 | 2.5 | Exporting Created Mood Boards
| 1.3.3.3 | Connect The Data Flow Process | Cindy | 0.5 | 0.25 | 2.5.1 | Implement Mood Board capture feature | Group | 2 | TBA
| 1.3.3.4 | Format Data Flow Diagram | Cindy | 0.25 | 0.25 | 2.5.2 | Develop custom export options | Group | 2 | TBA
| 1.3.4 | Project Schedule | Cindy |  |  | 2.5.3 | Add annotation features | Group | 1 | TBA
| 1.3.4.1 | Create a Detailed Outline of Schedule | Cindy | 1.5 | 2 | 2.5.4 | Exporting Created Mood Boards Complete |  | 5 | 0
| 1.3.4.2 | Duration/time frame for each task | Cindy | 2 | 1.5 | 2.6 | Testing & Debugging
| 1.3.4.3 | Idicate Tasks to Each Assignee | Cindy | 0.5 | 0.5 | 2.6.1 | Make general test cases | Group | 3 | TBA
| 1.3.4.4 | Schedule Organization | Cindy | 1 | 0.25 | 2.6.2 | Make specific/edge test cases | Group | 7 | TBA
| 1.3.5 | Early WBS | Stefan | 3 | 5.5 | 2.6.3 | Think of specific user profile cases | Group | 3 | TBA
| 1.3.6 | Project Plan Details Complete |  | 25.75 | 26.3 | 2.6.4 | General debugging | Group | 5 | TBA
| 1.4 | Initial Documentation |  |  |  | 2.6.5 | Testing & Debugging Complete |  | 18 | 0
| 1.4.1 | Create Project Report | Stefan | 3 | 5 | 2.7 | Documentation and finalizing
| 1.4.2 | Create presentation number 1 | Group | 1 | 1 | 2.7.1 | Check for general grammar or spelling errors | Group | 1 | TBA
| 1.4.3 | Establish team presenation roles | Group | 0.5 | 0.5 | 2.7.2 | Create a document which explains implementation | Group | 4 | TBA
| 1.4.4 | Check for spelling and correctness | Group | 0.5 | 0.5 | 2.7.3 | Make sure to have services for the user in need of support | Group | 2 | TBA
| 1.4.5 | Submit Report and Presenation 1 | Taiga |  |  | 2.7.4 | Transfer final project file state to github for submission | Group | 0.5 | TBA
| 1.4.6 | Initial Documentation Complete |  | 5 | 7 | 2.7.5 | Documentation and finalizing Complete |  | 7.5 | 0
| 1.5 | Project Planning Complete |  | 40.25 | 40.4 | 2.8 | Coding/Implementation Complete |  | 50.5 | 0
Color Pallete Generator
1 Project Planning
1.3 Project Plan Details
1.3.1 Create User Stories
2 Coding/Implementation
2.1 Import Necessary APIs
2.2 Create layout and general features
2.3 Implement main color extractor
2.1.1 Import Cloudinary
2.2.1
Develop header and navigation functionality
1.1 Team Setup
1.1.1 Establish team communication
1.1.2
Split up team roles and work assignment
1.2 Technical Requirements
1.2.1 SDLC Selection
1.2.2 Technology Stack Selection
1.2.3 Choose APIs for color extraction
1.2.4 Choose APIs for image uploading
1.2.5 Determine features for each API
1.2.6 Setup Github and Github Actions
1.2.7 Setup Figma, the work enviroment.
1.3.2 Wireframe and Prototype
1.3.3 Data Flow Diagram
1.3.4 Project Schedule
1.3.5 Early WBS
1.4 Initial Documentation
1.4.1 Create Project Report
1.4.2 Create presentation number 1
1.4.3 Establish team presenation roles
1.4.3 Record Presenation
1.4.5 Submit Report and Presenation 1
1.4.4 Check for spelling and correctness
2.1.2 Import Colormind
2.1.3 Import Imagga Color Extraction
2.3.1
Research color extraction algorithms
2.3.2 Select API for color extraction
2.3.3 Setup API Environment
2.3.4 Develop color extraction function
2.3.5 Integrate color extraction with frontend
2.3.6 Test color extraction feature
2.3.7 Implement error handling and edge cases
2.3.8 Test with users and collect feedback
2.4 Moodboard creation and Drag & Drop
2.4.1 Implement Drag & Drop functionality
2.4.2 Create Mood Board Arrangement features
2.5 Exporting Created Mood Boards
2.5.1 Implement Mood Board capture feature
2.5.2 Develop custom export options
2.6 Testing & Debugging
2.6.1 Make general test cases
2.6.2 Make specific/edge test cases
2.7 Documentation and finalizing
2.7.1 Check for general grammar or spelling errors
2.7.2 Create a document which explains implementation
3 Final Documentation
3.1
Create final project report
3.2 Create Final Presenation
3.3 Final Submission
3.1.1
Identify lessons learned from project
3.2.1
Create presentation slides
3.3.1
Check project requirements for web application
3.1.2
Include information which is required
3.1.3
Place necessary links and files
3.1.4
Final spelling and grammatical check
3.2.2
Create project demo video
3.2.3
Include information which is required
3.2.4
Practice presentation to stay in time limit
3.2.5
Record presenation
3.3.2
Check for general quality (spelling, grammar)
3.3.3
Check project requirements for report and presentation
3.3.4
Check for general quality (spelling, grammar)
3.3.5
Confirm repository has all required files
2.5.3 Add annotation features
2.6.3 Think of specific user profile cases
2.6.4 General debugging
2.7.3 Make sure to have services for the user in need of support
2.7.4 Transfer final project file state to github for submission
2.2.2
Test header and navigation functionality
2.2.3
Page structure and layout
2.2.4
Test page structure and layout
2.2.5
Error handling and validation
2.2.6
Export functionality
2.2.7
Saving functionality